## Sheet1
Possession Ref | Possession Ref_Flag | LOR | LOR_Flag | Possession Location from | Possession Location from_Flag | Possession Location to | Possession Location to_Flag | Blocked Line | Blocked Line_Flag | Protection Type | Protection Type_Flag | Start Date | Start Date_Flag | End Date | End Date_Flag | Traffic Remarks | Traffic Remarks_Flag | Work Type | Work Type_Flag | Week
P2022/2911551 |  | EA1360 EA1370 LN3201 LN3210 LN3213 LN3214 LN3219 LN3222 SO280 SO400 |  | Brent Curve Jn | 1 | Dudding Hill Jn | 1 | Down and Up Brent Curve | 1 | Possession | 1 | 10/12/22 2340 Sat | 1 | 11/12/22 0855 Sun | 1 | Bedford Maintenance Delivery Unit: Cyclical Maintenance 2340 SAT TO 0155 SUN TRAINS TO TRAVEL OVER THE SLOW LINES. 0155 SUN TO 0545 SUN NO BOOKED TRAFFIC. 0545 SUN TO 0345 MON THAMESLINK NORTH SIDE SERVICES TO START/TERMINATE AT ST.PANCRAS HIGH LEVEL (4TPH). TRAINS TO TRAVEL OVER THE FAST LINES BETWEEN DOCK JN AND CRICKLEWOOD SOUTH JN. | 2 |  |  | 37
P2022/2911551 |  | EA1360 EA1370 LN3201 LN3210 LN3213 LN3214 LN3219 LN3222 SO280 SO400 |  | Cricklewood Curve Jn | 1 | Dudding Hill Jn | 1 | Down and Up Cricklewood Curve | 1 | Possession | 1 | 10/12/22 2340 Sat | 1 | 11/12/22 0855 Sun | 1 | Bedford Maintenance Delivery Unit: Cyclical Maintenance 2340 SAT TO 0155 SUN TRAINS TO TRAVEL OVER THE SLOW LINES. 0155 SUN TO 0545 SUN NO BOOKED TRAFFIC. 0545 SUN TO 0345 MON THAMESLINK NORTH SIDE SERVICES TO START/TERMINATE AT ST.PANCRAS HIGH LEVEL (4TPH). TRAINS TO TRAVEL OVER THE FAST LINES BETWEEN DOCK JN AND CRICKLEWOOD SOUTH JN. | 2 |  |  | 37
P2022/2911551 |  | EA1360 EA1370 LN3201 LN3210 LN3213 LN3214 LN3219 LN3222 SO280 SO400 |  | Dock Jn North |  | Kentish Town Jn |  | Up & Down Relief |  | Possession |  | 10/12/22 2340 Sat |  | 12/12/22 0345 Mon |  | Bedford Maintenance Delivery Unit: Cyclical Maintenance 2340 SAT TO 0155 SUN TRAINS TO TRAVEL OVER THE SLOW LINES. 0155 SUN TO 0545 SUN NO BOOKED TRAFFIC. 0545 SUN TO 0345 MON THAMESLINK NORTH SIDE SERVICES TO START/TERMINATE AT ST.PANCRAS HIGH LEVEL (4TPH). TRAINS TO TRAVEL OVER THE FAST LINES BETWEEN DOCK JN AND CRICKLEWOOD SOUTH JN. | 2 |  |  | 37
P2022/2911551 |  | EA1360 EA1370 LN3201 LN3210 LN3213 LN3214 LN3219 LN3222 SO280 SO400 |  | Dock Jn South |  | Kentish Town Jn |  | Up & Down Slow |  | Possession |  | 10/12/22 2340 Sat |  | 12/12/22 0345 Mon |  | Bedford Maintenance Delivery Unit: Cyclical Maintenance 2340 SAT TO 0155 SUN TRAINS TO TRAVEL OVER THE SLOW LINES. 0155 SUN TO 0545 SUN NO BOOKED TRAFFIC. 0545 SUN TO 0345 MON THAMESLINK NORTH SIDE SERVICES TO START/TERMINATE AT ST.PANCRAS HIGH LEVEL (4TPH). TRAINS TO TRAVEL OVER THE FAST LINES BETWEEN DOCK JN AND CRICKLEWOOD SOUTH JN. | 2 |  |  | 37
P2022/2911551 |  | EA1360 EA1370 LN3201 LN3210 LN3213 LN3214 LN3219 LN3222 SO280 SO400 |  | Dudding Hill Jn | 1 | Neasden Jn | 1 | Down Goods Up Goods | 1 | Possession | 1 | 10/12/22 2340 Sat | 1 | 11/12/22 0855 Sun | 1 | Bedford Maintenance Delivery Unit: Cyclical Maintenance 2340 SAT TO 0155 SUN TRAINS TO TRAVEL OVER THE SLOW LINES. 0155 SUN TO 0545 SUN NO BOOKED TRAFFIC. 0545 SUN TO 0345 MON THAMESLINK NORTH SIDE SERVICES TO START/TERMINATE AT ST.PANCRAS HIGH LEVEL (4TPH). TRAINS TO TRAVEL OVER THE FAST LINES BETWEEN DOCK JN AND CRICKLEWOOD SOUTH JN. | 2 |  |  | 37
P2022/2911551 |  | EA1360 EA1370 LN3201 LN3210 LN3213 LN3214 LN3219 LN3222 SO280 SO400 |  | Hendon (London) | 1 | Silkstream Jn | 1 | Hendon Chord | 1 | Possession | 1 | 10/12/22 2340 Sat | 1 | 11/12/22 0855 Sun | 1 | Bedford Maintenance Delivery Unit: Cyclical Maintenance 2340 SAT TO 0155 SUN TRAINS TO TRAVEL OVER THE SLOW LINES. 0155 SUN TO 0545 SUN NO BOOKED TRAFFIC. 0545 SUN TO 0345 MON THAMESLINK NORTH SIDE SERVICES TO START/TERMINATE AT ST.PANCRAS HIGH LEVEL (4TPH). TRAINS TO TRAVEL OVER THE FAST LINES BETWEEN DOCK JN AND CRICKLEWOOD SOUTH JN. | 2 |  |  | 37
P2022/2911551 |  | EA1360 EA1370 LN3201 LN3210 LN3213 LN3214 LN3219 LN3222 SO280 SO400 |  | St. Pancras International |  | West Hampstead North Jn | 2 | Down & Up Fast | 2 | Possession |  | 10/12/22 2340 Sat |  | 11/12/22 0545 Sun | 2 | Bedford Maintenance Delivery Unit: Cyclical Maintenance 2340 SAT TO 0155 SUN TRAINS TO TRAVEL OVER THE SLOW LINES. 0155 SUN TO 0545 SUN NO BOOKED TRAFFIC. 0545 SUN TO 0345 MON THAMESLINK NORTH SIDE SERVICES TO START/TERMINATE AT ST.PANCRAS HIGH LEVEL (4TPH). TRAINS TO TRAVEL OVER THE FAST LINES BETWEEN DOCK JN AND CRICKLEWOOD SOUTH JN. | 2 |  |  | 37
P2022/2911551 |  | EA1360 EA1370 LN3201 LN3210 LN3213 LN3214 LN3219 LN3222 SO280 SO400 |  | West Hampstead South Jn | 1 | Silkstream Jn | 1 | Down and Up Hendon | 1 | Possession | 1 | 10/12/22 2340 Sat | 1 | 11/12/22 0855 Sun | 1 | Bedford Maintenance Delivery Unit: Cyclical Maintenance 2340 SAT TO 0155 SUN TRAINS TO TRAVEL OVER THE SLOW LINES. 0155 SUN TO 0545 SUN NO BOOKED TRAFFIC. 0545 SUN TO 0345 MON THAMESLINK NORTH SIDE SERVICES TO START/TERMINATE AT ST.PANCRAS HIGH LEVEL (4TPH). TRAINS TO TRAVEL OVER THE FAST LINES BETWEEN DOCK JN AND CRICKLEWOOD SOUTH JN. | 2 |  |  | 37
P2022/2911551 |  | EA1360 EA1370 LN3201 LN3210 LN3213 LN3214 LN3219 LN3222 SO280 SO400 |  | West Hampstead North Jn | 1 | Radlett Jn | 1 | Down & Up Fast | 1 | BLOCKED To A/C Electric Trains | 1 | 10/12/22 2340 Sat | 1 | 11/12/22 0545 Sun | 1 | Bedford Maintenance Delivery Unit: Cyclical Maintenance 2340 SAT TO 0155 SUN TRAINS TO TRAVEL OVER THE SLOW LINES. 0155 SUN TO 0545 SUN NO BOOKED TRAFFIC. 0545 SUN TO 0345 MON THAMESLINK NORTH SIDE SERVICES TO START/TERMINATE AT ST.PANCRAS HIGH LEVEL (4TPH). TRAINS TO TRAVEL OVER THE FAST LINES BETWEEN DOCK JN AND CRICKLEWOOD SOUTH JN. | 2 |  |  | 37
P2022/2911551 |  | EA1360 EA1370 LN3201 LN3210 LN3213 LN3214 LN3219 LN3222 SO280 SO400 |  | West Hampstead North Jn | 3 | Radlett Jn | 3 | Down & Up Fast | 3 | BLOCKED To Electric Trains | 3 | 10/12/22 2340 Sat | 3 | 11/12/22 0545 Sun | 3 | Bedford Maintenance Delivery Unit: Cyclical Maintenance 2340 SAT TO 0155 SUN TRAINS TO TRAVEL OVER THE SLOW LINES. 0155 SUN TO 0545 SUN NO BOOKED TRAFFIC. 0545 SUN TO 0345 MON THAMESLINK NORTH SIDE SERVICES TO START/TERMINATE AT ST.PANCRAS HIGH LEVEL (4TPH). TRAINS TO TRAVEL OVER THE FAST LINES BETWEEN DOCK JN AND CRICKLEWOOD SOUTH JN. | 2 |  |  | 37
P2022/2911551 |  | EA1360 EA1370 LN3201 LN3210 LN3213 LN3214 LN3219 LN3222 SO280 SO400 |  | Canal Tunnels Jn |  | Belle Isle Jn |  | Down and Up Canal Tunnel |  | Possession |  | 11/12/22 0155 Sun | 2 | 12/12/22 0345 Mon |  | Bedford Maintenance Delivery Unit: Cyclical Maintenance 2340 SAT TO 0155 SUN TRAINS TO TRAVEL OVER THE SLOW LINES. 0155 SUN TO 0545 SUN NO BOOKED TRAFFIC. 0545 SUN TO 0345 MON THAMESLINK NORTH SIDE SERVICES TO START/TERMINATE AT ST.PANCRAS HIGH LEVEL (4TPH). TRAINS TO TRAVEL OVER THE FAST LINES BETWEEN DOCK JN AND CRICKLEWOOD SOUTH JN. | 2 |  |  | 37
P2022/2911551 |  | EA1360 EA1370 LN3201 LN3210 LN3213 LN3214 LN3219 LN3222 SO280 SO400 |  | Carlton Road Jn |  | Junction Road Jn |  | Down and Up Tottenham |  | Possession |  | 11/12/22 0155 Sun | 2 | 12/12/22 0345 Mon |  | Bedford Maintenance Delivery Unit: Cyclical Maintenance 2340 SAT TO 0155 SUN TRAINS TO TRAVEL OVER THE SLOW LINES. 0155 SUN TO 0545 SUN NO BOOKED TRAFFIC. 0545 SUN TO 0345 MON THAMESLINK NORTH SIDE SERVICES TO START/TERMINATE AT ST.PANCRAS HIGH LEVEL (4TPH). TRAINS TO TRAVEL OVER THE FAST LINES BETWEEN DOCK JN AND CRICKLEWOOD SOUTH JN. | 2 |  |  | 37
P2022/2911551 |  | EA1360 EA1370 LN3201 LN3210 LN3213 LN3214 LN3219 LN3222 SO280 SO400 |  | Farringdon |  | Kentish Town Jn |  | Down and Up Moorgate |  | Possession |  | 11/12/22 0155 Sun | 2 | 12/12/22 0345 Mon |  | Bedford Maintenance Delivery Unit: Cyclical Maintenance 2340 SAT TO 0155 SUN TRAINS TO TRAVEL OVER THE SLOW LINES. 0155 SUN TO 0545 SUN NO BOOKED TRAFFIC. 0545 SUN TO 0345 MON THAMESLINK NORTH SIDE SERVICES TO START/TERMINATE AT ST.PANCRAS HIGH LEVEL (4TPH). TRAINS TO TRAVEL OVER THE FAST LINES BETWEEN DOCK JN AND CRICKLEWOOD SOUTH JN. | 2 |  |  | 37
P2022/2911551 |  | EA1360 EA1370 LN3201 LN3210 LN3213 LN3214 LN3219 LN3222 SO280 SO400 |  | Kentish Town Jn |  | West Hampstead Thameslink | 2 | Down and Up Slow |  | Possession |  | 11/12/22 0155 Sun | 2 | 12/12/22 0345 Mon | 2 | Bedford Maintenance Delivery Unit: Cyclical Maintenance 2340 SAT TO 0155 SUN TRAINS TO TRAVEL OVER THE SLOW LINES. 0155 SUN TO 0545 SUN NO BOOKED TRAFFIC. 0545 SUN TO 0345 MON THAMESLINK NORTH SIDE SERVICES TO START/TERMINATE AT ST.PANCRAS HIGH LEVEL (4TPH). TRAINS TO TRAVEL OVER THE FAST LINES BETWEEN DOCK JN AND CRICKLEWOOD SOUTH JN. | 2 |  |  | 37
P2022/2911551 |  | EA1360 EA1370 LN3201 LN3210 LN3213 LN3214 LN3219 LN3222 SO280 SO400 |  | West Hampstead Thameslink | 1 | Cricklewood South Jn | 1 | Down Carriage Loop | 1 | Possession | 1 | 11/12/22 0205 Sun | 1 | 11/12/22 0855 Sun | 1 | Bedford Maintenance Delivery Unit: Cyclical Maintenance 2340 SAT TO 0155 SUN TRAINS TO TRAVEL OVER THE SLOW LINES. 0155 SUN TO 0545 SUN NO BOOKED TRAFFIC. 0545 SUN TO 0345 MON THAMESLINK NORTH SIDE SERVICES TO START/TERMINATE AT ST.PANCRAS HIGH LEVEL (4TPH). TRAINS TO TRAVEL OVER THE FAST LINES BETWEEN DOCK JN AND CRICKLEWOOD SOUTH JN. | 2 |  |  | 37
P2022/2911551 |  | EA1360 EA1370 LN3201 LN3210 LN3213 LN3214 LN3219 LN3222 SO280 SO400 |  | Kentish Town Jn | 1 | Cricklewood South Jn | 1 | Down and Up Slow | 1 | Possession | 1 | 11/12/22 0855 Sun | 1 | 12/12/22 0345 Mon | 1 | Bedford Maintenance Delivery Unit: Cyclical Maintenance 2340 SAT TO 0155 SUN TRAINS TO TRAVEL OVER THE SLOW LINES. 0155 SUN TO 0545 SUN NO BOOKED TRAFFIC. 0545 SUN TO 0345 MON THAMESLINK NORTH SIDE SERVICES TO START/TERMINATE AT ST.PANCRAS HIGH LEVEL (4TPH). TRAINS TO TRAVEL OVER THE FAST LINES BETWEEN DOCK JN AND CRICKLEWOOD SOUTH JN. | 2 |  |  | 37
P2022/3465758 |  | SO400 |  | St. Pancras International |  | St. Pancras International |  | Platforms 5 to 13 |  | Possession |  | 11/12/22 0025 Sun |  | 11/12/22 0600 Sun |  | 3 PLATFORMS WILL REMAIN CLEAR FOR TRAINS TO BE STABLED IN ST.PANCRAS INTERNATIONAL. ANY STABLED TRAINS ARE REQUIRED TO PAN DOWN. NO ACCESS TO/FROM NLL OR ECML. NO ACCESS TO/FROM TEMPLE MILLS INTERNATIONAL DEPOT (MOVEMENTS WITHIN THE DEPOT NOT AFFECTED) |  |  |  | 37
P2022/3465758 |  | SO400 |  | St. Pancras International |  | Stratford International East Jn |  | All CTRL Lines |  | Possession |  | 11/12/22 0025 Sun |  | 11/12/22 0600 Sun |  | 3 PLATFORMS WILL REMAIN CLEAR FOR TRAINS TO BE STABLED IN ST.PANCRAS INTERNATIONAL. ANY STABLED TRAINS ARE REQUIRED TO PAN DOWN. NO ACCESS TO/FROM NLL OR ECML. NO ACCESS TO/FROM TEMPLE MILLS INTERNATIONAL DEPOT (MOVEMENTS WITHIN THE DEPOT NOT AFFECTED) |  |  |  | 37
P2022/3465758 |  | SO400 |  | Stratford International West Jn |  | Temple Mills International Depot |  | Single |  | Possession |  | 11/12/22 0025 Sun |  | 11/12/22 0600 Sun |  | 3 PLATFORMS WILL REMAIN CLEAR FOR TRAINS TO BE STABLED IN ST.PANCRAS INTERNATIONAL. ANY STABLED TRAINS ARE REQUIRED TO PAN DOWN. NO ACCESS TO/FROM NLL OR ECML. NO ACCESS TO/FROM TEMPLE MILLS INTERNATIONAL DEPOT (MOVEMENTS WITHIN THE DEPOT NOT AFFECTED) |  |  |  | 37
P2022/3464759 |  | SO400 |  | St. Pancras International |  | St. Pancras International |  | Platforms 5 to 13 |  | Possession |  | 12/12/22 0025 Mon |  | 12/12/22 0440 Mon |  | TRAINS MAY BE STABLED IN ST.PANCRAS INTERNATIONAL PLATFORMS. NO ACCESS TO/FROM NLL OR ECML. NO ACCESS TO/FROM TEMPLE MILLS INTERNATIONAL DEPOT (MOVEMENTS WITHIN THE DEPOT NOT AFFECTED) |  |  |  | 37
P2022/3464759 |  | SO400 |  | St. Pancras International |  | Stratford International East Jn |  | All CTRL Lines |  | Possession |  | 12/12/22 0025 Mon |  | 12/12/22 0440 Mon |  | TRAINS MAY BE STABLED IN ST.PANCRAS INTERNATIONAL PLATFORMS. NO ACCESS TO/FROM NLL OR ECML. NO ACCESS TO/FROM TEMPLE MILLS INTERNATIONAL DEPOT (MOVEMENTS WITHIN THE DEPOT NOT AFFECTED) |  |  |  | 37
P2022/3464759 |  | SO400 |  | Stratford International West Jn |  | Temple Mills International Depot |  | Single |  | Possession |  | 12/12/22 0025 Mon |  | 12/12/22 0440 Mon |  | TRAINS MAY BE STABLED IN ST.PANCRAS INTERNATIONAL PLATFORMS. NO ACCESS TO/FROM NLL OR ECML. NO ACCESS TO/FROM TEMPLE MILLS INTERNATIONAL DEPOT (MOVEMENTS WITHIN THE DEPOT NOT AFFECTED) |  |  |  | 37
P2022/3466103 |  | SO400 |  | St. Pancras International |  | St. Pancras International |  | Platforms 5 to 13 |  | Possession |  | 18/12/22 0025 Sun |  | 18/12/22 0600 Sun |  | 3 PLATFORMS WILL REMAIN CLEAR FOR TRAINS TO BE STABLED IN ST.PANCRAS INTERNATIONAL. ANY STABLED TRAINS ARE REQUIRED TO PAN DOWN. NO ACCESS TO/FROM NLL OR ECML. NO ACCESS TO/FROM TEMPLE MILLS INTERNATIONAL DEPOT (MOVEMENTS WITHIN THE DEPOT NOT AFFECTED) |  |  |  | 38
P2022/3466103 |  | SO400 |  | St. Pancras International |  | Stratford International East Jn |  | All CTRL Lines |  | Possession |  | 18/12/22 0025 Sun |  | 18/12/22 0600 Sun |  | 3 PLATFORMS WILL REMAIN CLEAR FOR TRAINS TO BE STABLED IN ST.PANCRAS INTERNATIONAL. ANY STABLED TRAINS ARE REQUIRED TO PAN DOWN. NO ACCESS TO/FROM NLL OR ECML. NO ACCESS TO/FROM TEMPLE MILLS INTERNATIONAL DEPOT (MOVEMENTS WITHIN THE DEPOT NOT AFFECTED) |  |  |  | 38
P2022/3466103 |  | SO400 |  | Stratford International West Jn |  | Temple Mills International Depot |  | Single |  | Possession |  | 18/12/22 0025 Sun |  | 18/12/22 0600 Sun |  | 3 PLATFORMS WILL REMAIN CLEAR FOR TRAINS TO BE STABLED IN ST.PANCRAS INTERNATIONAL. ANY STABLED TRAINS ARE REQUIRED TO PAN DOWN. NO ACCESS TO/FROM NLL OR ECML. NO ACCESS TO/FROM TEMPLE MILLS INTERNATIONAL DEPOT (MOVEMENTS WITHIN THE DEPOT NOT AFFECTED) |  |  |  | 38
P2022/3464882 |  | SO400 |  | St. Pancras International |  | St. Pancras International |  | Platforms 5 to 13 |  | Possession |  | 19/12/22 0025 Mon |  | 19/12/22 0440 Mon |  | TRAINS MAY BE STABLED IN ST.PANCRAS INTERNATIONAL PLATFORMS. NO ACCESS TO/FROM NLL OR ECML. NO ACCESS TO/FROM TEMPLE MILLS INTERNATIONAL DEPOT (MOVEMENTS WITHIN THE DEPOT NOT AFFECTED) |  |  |  | 38
P2022/3464882 |  | SO400 |  | St. Pancras International |  | Stratford International East Jn |  | All CTRL Lines |  | Possession |  | 19/12/22 0025 Mon |  | 19/12/22 0440 Mon |  | TRAINS MAY BE STABLED IN ST.PANCRAS INTERNATIONAL PLATFORMS. NO ACCESS TO/FROM NLL OR ECML. NO ACCESS TO/FROM TEMPLE MILLS INTERNATIONAL DEPOT (MOVEMENTS WITHIN THE DEPOT NOT AFFECTED) |  |  |  | 38
P2022/3464882 |  | SO400 |  | Stratford International West Jn |  | Temple Mills International Depot |  | Single |  | Possession |  | 19/12/22 0025 Mon |  | 19/12/22 0440 Mon |  | TRAINS MAY BE STABLED IN ST.PANCRAS INTERNATIONAL PLATFORMS. NO ACCESS TO/FROM NLL OR ECML. NO ACCESS TO/FROM TEMPLE MILLS INTERNATIONAL DEPOT (MOVEMENTS WITHIN THE DEPOT NOT AFFECTED) |  |  |  | 38
P2022/3468582 | 3 | EA1180 EA1310 EA1320 EA1340 LN110 LN115 MD145 SO400 |  | Camden Road Central Jn |  | Camden Road Incline Jn |  | North London Incline |  | Possession |  | 18/12/22 0045 Sun | 2 | 18/12/22 0850 Sun | 2 | GTR WILL BE REVERSING TRAINS AT HIGHBURY VALE AS A RESULT OF A SECTION 7 ON EAST COAST NLL CYCLIC TYPE 7A (ROTR) | 3 | W2022/9270992 URFDO Inspections 3m20ch and 4m40ch W2022/9270893 Track Maintenance 3m20ch and 4m40ch | 3 | 38
P2022/3468582 |  | EA1180 EA1310 EA1320 EA1340 LN110 LN115 MD145 SO400 |  | Camden Road East Jn |  | Highbury and Islington |  | Down North London Relief Up North London Reversible |  | Possession |  | 18/12/22 0045 Sun | 2 | 18/12/22 0850 Sun | 2 | GTR WILL BE REVERSING TRAINS AT HIGHBURY VALE AS A RESULT OF A SECTION 7 ON EAST COAST NLL CYCLIC TYPE 7A (ROTR) | 3 | W2022/9270992 URFDO Inspections 3m20ch and 4m40ch W2022/9270893 Track Maintenance 3m20ch and 4m40ch |  | 38
P2022/3468582 |  | EA1180 EA1310 EA1320 EA1340 LN110 LN115 MD145 SO400 |  | Camden Road West Jn |  | Channelsea North Jn |  | Down and Up North London |  | Possession |  | 18/12/22 0045 Sun | 2 | 18/12/22 0850 Sun | 2 | GTR WILL BE REVERSING TRAINS AT HIGHBURY VALE AS A RESULT OF A SECTION 7 ON EAST COAST NLL CYCLIC TYPE 7A (ROTR) | 3 | W2022/9270992 URFDO Inspections 3m20ch and 4m40ch W2022/9270893 Track Maintenance 3m20ch and 4m40ch |  | 38
P2022/3468582 |  | EA1180 EA1310 EA1320 EA1340 LN110 LN115 MD145 SO400 |  | Canonbury West Jn |  | Highbury Vale Jn |  | Up/Down Canonbury |  | Possession |  | 18/12/22 0045 Sun | 2 | 18/12/22 0850 Sun | 2 | GTR WILL BE REVERSING TRAINS AT HIGHBURY VALE AS A RESULT OF A SECTION 7 ON EAST COAST NLL CYCLIC TYPE 7A (ROTR) | 3 | W2022/9270992 URFDO Inspections 3m20ch and 4m40ch W2022/9270893 Track Maintenance 3m20ch and 4m40ch |  | 38
P2022/3468582 |  | EA1180 EA1310 EA1320 EA1340 LN110 LN115 MD145 SO400 |  | Cedar Jn |  | Cedar Jn |  | Silo Curve |  | Possession |  | 18/12/22 0045 Sun | 2 | 18/12/22 0850 Sun | 2 | GTR WILL BE REVERSING TRAINS AT HIGHBURY VALE AS A RESULT OF A SECTION 7 ON EAST COAST NLL CYCLIC TYPE 7A (ROTR) | 3 | W2022/9270992 URFDO Inspections 3m20ch and 4m40ch W2022/9270893 Track Maintenance 3m20ch and 4m40ch |  | 38
P2022/3468582 |  | EA1180 EA1310 EA1320 EA1340 LN110 LN115 MD145 SO400 |  | Gospel Oak Jn |  | Camden Road West Jn |  | Down and Up North London |  | Possession |  | 18/12/22 0045 Sun | 2 | 18/12/22 0850 Sun | 2 | GTR WILL BE REVERSING TRAINS AT HIGHBURY VALE AS A RESULT OF A SECTION 7 ON EAST COAST NLL CYCLIC TYPE 7A (ROTR) | 3 | W2022/9270992 URFDO Inspections 3m20ch and 4m40ch W2022/9270893 Track Maintenance 3m20ch and 4m40ch |  | 38
P2022/3468582 |  | EA1180 EA1310 EA1320 EA1340 LN110 LN115 MD145 SO400 |  | Lea Jn |  | High Meads Jn |  | Down and Up Lea Curve |  | Possession |  | 18/12/22 0045 Sun | 2 | 18/12/22 0850 Sun | 2 | GTR WILL BE REVERSING TRAINS AT HIGHBURY VALE AS A RESULT OF A SECTION 7 ON EAST COAST NLL CYCLIC TYPE 7A (ROTR) | 3 | W2022/9270992 URFDO Inspections 3m20ch and 4m40ch W2022/9270893 Track Maintenance 3m20ch and 4m40ch |  | 38
P2022/3468582 |  | EA1180 EA1310 EA1320 EA1340 LN110 LN115 MD145 SO400 |  | Navarino Road Jn |  | Reading Lane Jn |  | Graham Road Curve |  | Possession |  | 18/12/22 0045 Sun | 2 | 18/12/22 0850 Sun | 2 | GTR WILL BE REVERSING TRAINS AT HIGHBURY VALE AS A RESULT OF A SECTION 7 ON EAST COAST NLL CYCLIC TYPE 7A (ROTR) | 3 | W2022/9270992 URFDO Inspections 3m20ch and 4m40ch W2022/9270893 Track Maintenance 3m20ch and 4m40ch |  | 38
P2022/3468582 |  | EA1180 EA1310 EA1320 EA1340 LN110 LN115 MD145 SO400 |  | Primrose Hill (closed) site of |  | Camden Road West Jn |  | Down and Up North London |  | Possession |  | 18/12/22 0045 Sun | 2 | 18/12/22 0850 Sun | 2 | GTR WILL BE REVERSING TRAINS AT HIGHBURY VALE AS A RESULT OF A SECTION 7 ON EAST COAST NLL CYCLIC TYPE 7A (ROTR) | 3 | W2022/9270992 URFDO Inspections 3m20ch and 4m40ch W2022/9270893 Track Maintenance 3m20ch and 4m40ch |  | 38
P2022/3468582 |  | EA1180 EA1310 EA1320 EA1340 LN110 LN115 MD145 SO400 |  | Stratford Central Jn West |  | Lea Jn |  | Up Channelsea Loop |  | Possession |  | 18/12/22 0045 Sun | 2 | 18/12/22 0850 Sun | 2 | GTR WILL BE REVERSING TRAINS AT HIGHBURY VALE AS A RESULT OF A SECTION 7 ON EAST COAST NLL CYCLIC TYPE 7A (ROTR) | 3 | W2022/9270992 URFDO Inspections 3m20ch and 4m40ch W2022/9270893 Track Maintenance 3m20ch and 4m40ch |  | 38
P2022/3281582 |  | SO110 SO140 SO460 |  | Bickley Jn |  | Kemsing |  | Down Chatham Fast/Down Maidstone Up Maidstone/Up Chatham Fast |  | Possession |  | 18/12/22 0140 Sun |  | 19/12/22 0410 Mon |  | CHANNEL TUNNEL FREIGHT TO RUN VIA REDHILL. GTR BLACKFRIARS TO SEVENOAKS SERVICES DIVERTED TO ORPINGTON. SOUTHEASTERN VICTORIA TO RAMSGATE / DOVER SERVICES DIVERTED VIA DARTFORD/GRAVESEND SOUTHEASTERN VICTORIA TO ASHFORD INTERNATIONAL SERVICES TO RUN AS A SHUTTLE BETWEEN BOROUGH GREEN AND ASHFORD. UP TRAINS TO TERMINATE AT BOROUGH GREEN, SHUNT VIA ME404 POINTS, AND START BACK FROM THE DOWN PLATFORM. REPLACEMENT BUSES TO RUN BETWEEN BROMLEY SOUTH AND STROOD, AND BETWEEN BROMLEY SOUTH AND BOROUGH GREEN / SEVENOAKS WORK: Orpington DU - TRACK MAINTENANCE WORK: Ashford DU - TRACK MAINTENANCE (1 of 4). SCD Buildings: Footbridge remedial works Sole Street Station. SCD Telecomms: DOO equipment Eynsford, Otford, Shoreham and Swanley. |  |  |  | 38
P2022/3281582 |  | SO110 SO140 SO460 |  | Bickley Jn |  | Rochester Bridge Jn |  | Down Chatham Slow/Down Chatham Main/Down Chatham Up Chatham/Up Chatham Main/Up Chatham Slow |  | Possession |  | 18/12/22 0140 Sun |  | 19/12/22 0410 Mon |  | CHANNEL TUNNEL FREIGHT TO RUN VIA REDHILL. GTR BLACKFRIARS TO SEVENOAKS SERVICES DIVERTED TO ORPINGTON. SOUTHEASTERN VICTORIA TO RAMSGATE / DOVER SERVICES DIVERTED VIA DARTFORD/GRAVESEND SOUTHEASTERN VICTORIA TO ASHFORD INTERNATIONAL SERVICES TO RUN AS A SHUTTLE BETWEEN BOROUGH GREEN AND ASHFORD. UP TRAINS TO TERMINATE AT BOROUGH GREEN, SHUNT VIA ME404 POINTS, AND START BACK FROM THE DOWN PLATFORM. REPLACEMENT BUSES TO RUN BETWEEN BROMLEY SOUTH AND STROOD, AND BETWEEN BROMLEY SOUTH AND BOROUGH GREEN / SEVENOAKS WORK: Orpington DU - TRACK MAINTENANCE WORK: Ashford DU - TRACK MAINTENANCE (1 of 4). SCD Buildings: Footbridge remedial works Sole Street Station. SCD Telecomms: DOO equipment Eynsford, Otford, Shoreham and Swanley. |  |  |  | 38
P2022/3281582 |  | SO110 SO140 SO460 |  | Chislehurst Jn |  | St. Mary Cray Jn |  | Reversible Chatham Loop |  | Possession |  | 18/12/22 0140 Sun |  | 19/12/22 0410 Mon |  | CHANNEL TUNNEL FREIGHT TO RUN VIA REDHILL. GTR BLACKFRIARS TO SEVENOAKS SERVICES DIVERTED TO ORPINGTON. SOUTHEASTERN VICTORIA TO RAMSGATE / DOVER SERVICES DIVERTED VIA DARTFORD/GRAVESEND SOUTHEASTERN VICTORIA TO ASHFORD INTERNATIONAL SERVICES TO RUN AS A SHUTTLE BETWEEN BOROUGH GREEN AND ASHFORD. UP TRAINS TO TERMINATE AT BOROUGH GREEN, SHUNT VIA ME404 POINTS, AND START BACK FROM THE DOWN PLATFORM. REPLACEMENT BUSES TO RUN BETWEEN BROMLEY SOUTH AND STROOD, AND BETWEEN BROMLEY SOUTH AND BOROUGH GREEN / SEVENOAKS WORK: Orpington DU - TRACK MAINTENANCE WORK: Ashford DU - TRACK MAINTENANCE (1 of 4). SCD Buildings: Footbridge remedial works Sole Street Station. SCD Telecomms: DOO equipment Eynsford, Otford, Shoreham and Swanley. |  |  |  | 38
P2022/3281582 |  | SO110 SO140 SO460 |  | Fawkham Jn |  | Hook Green |  | Up Waterloo Connection Down Waterloo Connection |  | Possession |  | 18/12/22 0140 Sun |  | 19/12/22 0410 Mon |  | CHANNEL TUNNEL FREIGHT TO RUN VIA REDHILL. GTR BLACKFRIARS TO SEVENOAKS SERVICES DIVERTED TO ORPINGTON. SOUTHEASTERN VICTORIA TO RAMSGATE / DOVER SERVICES DIVERTED VIA DARTFORD/GRAVESEND SOUTHEASTERN VICTORIA TO ASHFORD INTERNATIONAL SERVICES TO RUN AS A SHUTTLE BETWEEN BOROUGH GREEN AND ASHFORD. UP TRAINS TO TERMINATE AT BOROUGH GREEN, SHUNT VIA ME404 POINTS, AND START BACK FROM THE DOWN PLATFORM. REPLACEMENT BUSES TO RUN BETWEEN BROMLEY SOUTH AND STROOD, AND BETWEEN BROMLEY SOUTH AND BOROUGH GREEN / SEVENOAKS WORK: Orpington DU - TRACK MAINTENANCE WORK: Ashford DU - TRACK MAINTENANCE (1 of 4). SCD Buildings: Footbridge remedial works Sole Street Station. SCD Telecomms: DOO equipment Eynsford, Otford, Shoreham and Swanley. |  |  |  | 38
P2022/3281582 |  | SO110 SO140 SO460 |  | Hawkwood Jn |  | Chislehurst Jn |  | Up Chatham Loop(pt) |  | Possession |  | 18/12/22 0140 Sun |  | 19/12/22 0410 Mon |  | CHANNEL TUNNEL FREIGHT TO RUN VIA REDHILL. GTR BLACKFRIARS TO SEVENOAKS SERVICES DIVERTED TO ORPINGTON. SOUTHEASTERN VICTORIA TO RAMSGATE / DOVER SERVICES DIVERTED VIA DARTFORD/GRAVESEND SOUTHEASTERN VICTORIA TO ASHFORD INTERNATIONAL SERVICES TO RUN AS A SHUTTLE BETWEEN BOROUGH GREEN AND ASHFORD. UP TRAINS TO TERMINATE AT BOROUGH GREEN, SHUNT VIA ME404 POINTS, AND START BACK FROM THE DOWN PLATFORM. REPLACEMENT BUSES TO RUN BETWEEN BROMLEY SOUTH AND STROOD, AND BETWEEN BROMLEY SOUTH AND BOROUGH GREEN / SEVENOAKS WORK: Orpington DU - TRACK MAINTENANCE WORK: Ashford DU - TRACK MAINTENANCE (1 of 4). SCD Buildings: Footbridge remedial works Sole Street Station. SCD Telecomms: DOO equipment Eynsford, Otford, Shoreham and Swanley. |  |  |  | 38
P2022/3281582 |  | SO110 SO140 SO460 |  | Otford Jn |  | Otford Jn |  | Up Goods Loop |  | Possession |  | 18/12/22 0140 Sun |  | 19/12/22 0410 Mon |  | CHANNEL TUNNEL FREIGHT TO RUN VIA REDHILL. GTR BLACKFRIARS TO SEVENOAKS SERVICES DIVERTED TO ORPINGTON. SOUTHEASTERN VICTORIA TO RAMSGATE / DOVER SERVICES DIVERTED VIA DARTFORD/GRAVESEND SOUTHEASTERN VICTORIA TO ASHFORD INTERNATIONAL SERVICES TO RUN AS A SHUTTLE BETWEEN BOROUGH GREEN AND ASHFORD. UP TRAINS TO TERMINATE AT BOROUGH GREEN, SHUNT VIA ME404 POINTS, AND START BACK FROM THE DOWN PLATFORM. REPLACEMENT BUSES TO RUN BETWEEN BROMLEY SOUTH AND STROOD, AND BETWEEN BROMLEY SOUTH AND BOROUGH GREEN / SEVENOAKS WORK: Orpington DU - TRACK MAINTENANCE WORK: Ashford DU - TRACK MAINTENANCE (1 of 4). SCD Buildings: Footbridge remedial works Sole Street Station. SCD Telecomms: DOO equipment Eynsford, Otford, Shoreham and Swanley. |  |  |  | 38
P2022/3281582 |  | SO110 SO140 SO460 |  | Otford Jn |  | Sevenoaks |  | Down Bat and Ball Up Bat and Ball |  | Possession |  | 18/12/22 0140 Sun |  | 19/12/22 0410 Mon |  | CHANNEL TUNNEL FREIGHT TO RUN VIA REDHILL. GTR BLACKFRIARS TO SEVENOAKS SERVICES DIVERTED TO ORPINGTON. SOUTHEASTERN VICTORIA TO RAMSGATE / DOVER SERVICES DIVERTED VIA DARTFORD/GRAVESEND SOUTHEASTERN VICTORIA TO ASHFORD INTERNATIONAL SERVICES TO RUN AS A SHUTTLE BETWEEN BOROUGH GREEN AND ASHFORD. UP TRAINS TO TERMINATE AT BOROUGH GREEN, SHUNT VIA ME404 POINTS, AND START BACK FROM THE DOWN PLATFORM. REPLACEMENT BUSES TO RUN BETWEEN BROMLEY SOUTH AND STROOD, AND BETWEEN BROMLEY SOUTH AND BOROUGH GREEN / SEVENOAKS WORK: Orpington DU - TRACK MAINTENANCE WORK: Ashford DU - TRACK MAINTENANCE (1 of 4). SCD Buildings: Footbridge remedial works Sole Street Station. SCD Telecomms: DOO equipment Eynsford, Otford, Shoreham and Swanley. |  |  |  | 38
P2022/3281582 |  | SO110 SO140 SO460 |  | St. Mary Cray Jn |  | Hawkwood Jn |  | Up Chatham Loop(pt) |  | Possession |  | 18/12/22 0140 Sun |  | 19/12/22 0410 Mon |  | CHANNEL TUNNEL FREIGHT TO RUN VIA REDHILL. GTR BLACKFRIARS TO SEVENOAKS SERVICES DIVERTED TO ORPINGTON. SOUTHEASTERN VICTORIA TO RAMSGATE / DOVER SERVICES DIVERTED VIA DARTFORD/GRAVESEND SOUTHEASTERN VICTORIA TO ASHFORD INTERNATIONAL SERVICES TO RUN AS A SHUTTLE BETWEEN BOROUGH GREEN AND ASHFORD. UP TRAINS TO TERMINATE AT BOROUGH GREEN, SHUNT VIA ME404 POINTS, AND START BACK FROM THE DOWN PLATFORM. REPLACEMENT BUSES TO RUN BETWEEN BROMLEY SOUTH AND STROOD, AND BETWEEN BROMLEY SOUTH AND BOROUGH GREEN / SEVENOAKS WORK: Orpington DU - TRACK MAINTENANCE WORK: Ashford DU - TRACK MAINTENANCE (1 of 4). SCD Buildings: Footbridge remedial works Sole Street Station. SCD Telecomms: DOO equipment Eynsford, Otford, Shoreham and Swanley. |  |  |  | 38